## Slide 1: Beyond Boundaries: Culture of Inclusion
Objective: Attract, retain and graduate a diverse and inclusive community of students
Objective: Attract and retain a diverse and inclusive community of faculty and staff committed to our mission
Objective: Enhance opportunities for diverse and inclusive learning and scholarship
Objective: Function as a community that values, respects, welcomes, and promotes a sense of belonging to all members
Objective: Engage diverse communities beyond the boundaries of our campus

## Slide 2: Diversity and Inclusion Planning Template: Four Frames
Representation
Environment (Internal Engagement)
Scholarship & Learning
Engaging Diverse Communities

## Slide 3: Diederich Goals for Representation
Goal 1: Increase number of students of color in first year class
  Mid-October 2020 – Formulate a data informed strategy for recruitment of diverse student population
    Research current state of first year class, identify opportunities and barriers
    Review plan on annual basis
  Fall 2021 Class – Target 30% of class students of color
  Fall 2022 Class – Target 32%
  Fall 2023 class – Target 35%
Goal 2: Implement specific strategy for recruitment and retention of diverse staff and faculty
  Establish recruitment guidelines for staff and faculty by Spring 2021
    Target 40% by 2025
  Identify barriers to and best practices for faculty retention (e.g., mentoring) by Feb 2021; establish strategies by May 2021; Implement Fall 2021

## Slide 4: Diederich Goal for Environment
Goal 1: Increase representation in student participation of co-curricular activities and leadership
  Audit student participation in college sponsored clubs, student media, C-Lead, student agency, O’Brien, MUPS, music ensembles, etc. by Mid -October 2020
  Set targets for growth to be measured in Dec 2020 (to be measures in Dec 2021)
  Develop specific mentoring and recruitment strategies by Dec 2020
Goal 2: Provide ongoing training and workshops for student involvement in diversity and inclusion programs
  Provide student facing workshop once per semester begin Fall 2020
  Leadership training/mentoring for student leaders on inclusion begin Fall 2020
(cont. on next slide)

## Slide 5: Diederich Goal for Environment
Goal 3: Implement a faculty development program on equity and inclusion
  College wide workshop/training once per semester during regularly scheduled meeting
  Increase faculty participation in workshops and programming outside college
    50% of faculty attended program (university symposium, Unlearning Racism, reading group, etc.) by May of 2021
    65% participation by May of 2022
    85% participation by May of 2023
Goal 4: Coordinate consistent messages across college platforms and spaces that are welcoming, inclusive, and accessible for all
  Audit website, speakers, programming for inclusive language and topics by Spring of 2021
  Develop protocol to evaluate programming and content choices by May 2021
  Audit spaces for accessibility by January 2021 (continue annually); Develop strategy to improve spaces by May 2021

## Slide 6: Diederich Goal for Scholarship & Learning
Goal 1: Increase research that focus on needs of underrepresented populations
  Audit of current research by Feb 2021
  Plan for incentivizing work by May 2021
  Set benchmarks by May 2021 to be measured Feb of 2023
Goal 2: Intentional recruitment practices to ensure hiring faculty who are prepared to teach in a diverse and inclusive classroom.
  Protocol for construction of job ads and recruitment plans (August 2021)
  Guideline for interviewing/ campus visit practices (November 2021)
  Selection criteria (November 2021)
Goal 3: Ensure use of inclusive design in course design and instruction.
  Audit of syllabi for use of inclusive design principles:
    25% of required courses by May 2021
    50% of required course by May 2022
    75% of required course by May 2023

## Slide 7: Diederich Goal for Engaging Diverse Communities
Goal 1: Develop a research culture that embraces community-based research
  Create structures to identify potential community partners for research projects
    Plan by Fall 2022
  Incentivize community-based research (Grad committee)
    Plan by May 2021
  Develop specific criteria for including community-based research and activity in promotion and tenure process.
    Fall 2022
Goal 2: Create educational and professional opportunities for students to engage with diverse communities
Diederich experiences focused on diverse communities (e.g., Univision)
  One f2f experience a year beginning Spring 2022
  One digital experience beginning Spring 2020
Create community-based research and creative practicum for grad and undergrad students.
  Fall 2022 (first offering)
Career workshops and/or fairs based on community-based organizations
  Spring 2020