## TCO Checklist
Terminal Closeout Checklist
Important Resources: |  |  | BI Report Guidance
Roles and Responsibilities
Managing an Award
Post Award Training Videos
PI Post-Award Checklist
PI
Project Title
Sponsor/Prime Sponsor
Sponsor Award Number
Total Project Dates (total anticipated period of project)
Account Number *If your award has multiple accounts (i.e., participant support, sub-projects, cost share) please review all accounts as part of this process |  |  | xx-xxxxx-7xxxx
Obligated Award Amount (amount currently available to spend) |  |  | Obligated Direct: $
Obligated FA: $
Obligated Total Award: $
F&A Rate: xx.x%
120 - 90 DAYS PRIOR TO AWARD END DATE
Use the following guidance to understand your current budget, funds remaining, and project spending through the current project end date.
Based on your projected findings, you will either: a) be spending out funds during the original project period and continue to complete the Terminal Closeout Checklist or b) if you have projected funds remaining after the original project end date and there is work to be done, begin the process of applying for a No Cost Extension.
Business Intelligence (BI) Resources Needed to Develop Spending Plan
FALSE | Access your Business Intelligence Report entitled "Grant Project Statement" | · | To access your most recent "closed" month Grant Project Statement, go to:
> dataMarq // Marquette University
Click here view How to Access Grant (Project) Statement tutorial
FALSE | Run latest Labor Distribution Report if your award has any payroll expenses *If you have federal work study students you must also run a FWS Matching Report | · | If your award has payroll expenses, review personnel paid on the grant and ensure that each employee or student that has been paid belongs on the grant and has been paid appropriately (timeframe and amounts)
|  | · | Any positions that will be terminated at the end of the grant where the employee does not have another position lined up at MU, their accumulated vacation time will be paid out by the grant. If your grant balance cannot accommodate vacation time, you have the option to instruct the individual to use the vacation prior to the terminal end date.
Click here to view How to Access Labor Distribution Report tutorial
FALSE | Run Journal Entries with iExpense Report Detail-Grants | · | If your award has operating expenses, review all items paid to ensure accuracy and completeness. Check to make sure everything you know you have purchased is accounted for.
|  | · | If you have purchased or plan to purchase any subscriptions, licenses or warraties with grant funds that extend beyond the terminal end date, you will need to find a new account to charge.
FALSE | Run Encumbrance Report if encumbrances are noted on Grant Project Statement | · | Check that order items have all been actually received and that all items for the order have been "Received" in MARQetplace. If not actually received, check in with vendor on order status (e.g., item(s) are on the way or item(s) are delayed/backordered). If the item(s) are on the way, monitor the order status closely so that you can receive on item(s) in MARQetplace and check that the invoice is received and processed so that items are paid for during the time that grant funds are available for payment. If the item(s) are delayed/backordered past your Project End date, you will need to work with the vendor and MU's Purchasing Dept.: i) if some of the items on the PO number have been received, but some will not be received before the grant Project End date, work with the vendor to cancel item(s) that won't be recieved in time and work with MU's Purchasing Dept. to close the order. ii) if all item(s) will not be received in time for the grant funds to pay for it, work with the vendor to cancel the order and work with MU's Purchasing Dept. to close the PO number.
|  | · | Check that the invoice has been processed by Accounts Payable.
|  | · | If an invoice is needed, reach out to the vendor for an invoice and send the invoice to Accounts Payable for processing.
Kuali Resources Needed to Develop Spending Plan
FALSE | Access sponsor approved budget | · | Your Sponsor Approved Budget can be found in Kuali under Awards Attachments
|  | · | Access Kuali using this link: Research Dashboard - Common Tasks
>To view/search awards, refer to this document
Develop Spending Plan
Spending Plan: Detailed plan to fully and appropriately use remaining funds by the initial end date to meet the objectives of the award and estimate amount of funds remaining at the initial project end date.
COMPENSATION
FALSE | Define personnel and fringe benefits yet to be paid through the existing project period | · | If your award has payroll expenses, review personnel paid on the grant using the Labor Distribution Report to ensure that each employee or student that has been paid belongs on the grant and has been paid appropriately (timeframe and amounts).
|  | · | List all future payroll anticipated through the end of the project period. Keep in mind that salaries are paid after the time period that work is performed in.
|  | · | Calculate fringes on payroll listed above
> Current fringe benefits rate document can be found here under Additional Information
> General payroll schedule can be found here
|  | · | Reach out to your college Business Director if any corrections/adjustments need to be made.
|  | · | If staff will be terminated at the end of the project, reach out to your college Business Director to begin termination process.
**Please note that for any positions that will be terminated at the end of the grant and do not have another position lined up at MU, their accumulated vacation time will be paid out by the grant
|  | · | If you have federal work study payroll expense match (6065) expenses, you must repeat this process using the FWS Matching Report.
OPERATING
FALSE | Lab or Office Supplies, travel, equipment, human/animal payments, publications, Consultants/Other Participants *Items purchased must be used within the project period. Prepayment for items used after the project end date are not allowable. These include publication costs, airline tickets, hotel reservations, etc. | · | Review your Journal Entries with iExpense Report Detail report to ensure accuracy and completeness. Check to make sure everything you know you have purchased is accounted for.
|  | · | List all future estimated operating costs through the end of the project period.
|  | · | Review open encumbrances and refer to:
> Business Intelligence (BI) Guidance
|  | · | Equipment purchases during the final 120 days needs to be allowable and allocable in the final stages of the award. (E.g., the equipment must be received and used in a meaningful way before the end date.)
|  | · | The portion of service contracts that are allowable and allocable must cover dates within the project period. (E.g., licenses that extend past the end date will be prorated.)
|  | · | Ensure all payments are processed.
|  | · | Confirm consultant's deliverables are on track and invoices are current as stated in the previously executed agreement.
|  | · | Estimate outstanding pcard purchases.
|  | · | Estimate outstanding internal cost center charges (i.e., animal care facility, dexa scans).
|  | · | Start the reconciliation process for any open travel advances.
|  | · | Pay particular attention to capital equipment purchases, service contracts, and large supply purchases in the last year of the project as they will receive a high level of scrutiny and MAY be disallowed during sponsor review or audit.
FALSE | Subaward Review | · | Know when subaward and final invoices are due. Verify that total payments made are current and all invoices received have been processed and reflected in the project statement. Also verify proper division between natural 6515 (subawards < $25,000) and 6520 (subawards > $25,000) to ensure proper indirect costs are charged.
|  | · | Account for future subaward invoices.
|  | · | Request technical report contributions as stated in the subaward agreement.
|  | · | Remind of any additional reporting (e.g., Intellectual Property, tangiblbe property, personnel reports).
FALSE | Consultants/Other Participants Review
Confirm deliverables are on track.
Ensure all payments are processed.
Request technical report contributions if applicable.
Move up in document and add to BI guidance
If unable to meet the objectives of the award by initial end date and funds remain, please proceed to No Cost Extension Guidelines below to explore a No Cost Extension (NCE) option. Go to XXXXX to complete No Cost Extension request form.
TUITION
FALSE | Student Tuition Review | · | Contact postaward@marquette.edu for a detailed list of student tuition paid per term.
|  | · | Verify it is complete and accurate. Inform ORSP if corrections are needed.
|  | · | List all future tuition needs and complete the Student Grant Support form for processing.
INDIRECT COST
FALSE | Indirect Cost Review *Reminder indirect costs are charged as direct costs are expensed. For example when a charge hits the project statement there should be associated indirect cost entry | · | Know the indirect cost rate. This can be found at the top of the Grant Project Statement.
|  | · | Verify the amount charged is accurate.
|  | · | Be sure to include future indirects in your spending plan.
|  | · | In your final spending plan be sure the applicable associated costs are accounted for when moving funds, compliant with sponsor guidelines, from non-indirect bearing items to indirect bearing items and vice versa (i.e., if moving funds from large equipment to supplies you must account for additional indirect costs. If moving from supplies to large equipment you have additional funds to work with).
After determining your spending plan, if funds remain, please refer to the No Cost Extension (NCE) resources below.
NO COST EXTENSION (NCE)
FALSE | Determine if No Cost Extension is needed | · | If unable to meet the objectives of the award by the initial end date and funds remain, please proceed to No Cost Extension (NCE) Guidelines below to explore and request a NCE.
> No Cost Extension (NCE) Guidelines
90-60 DAYS PRIOR TO AWARD END DATE
Repeat 120-90 day steps | [5 empty] | .
60-30 DAYS PRIOR TO AWARD END DATE
Repeat 120-90 day steps
FALSE |  | · | If you have analyzed your account in the past month and anything has changed in the last 30 days, recalculate (e.g., emplyees leaving or change in work status, supplies or equipment being backordered, prior estimated costs being higher or lower than anticipated, etc.)
FALSE |  | · | Start reviewing required closeout documents/preparing necessary reports
FALSE |  | · | Notify the Office of the Comptroller of your timeframe for submission so they can prepare the financial components accordingly; cc postaward@marquette.edu
FALSE |  | · | If there have been any changes that would now necessitate a no cost extension, please submit a request at:
> No Cost Extension (NCE) Request Form
FALSE |  | · | Avoid large purchases that may be disallowed during audit. Any item purchased on a grant must be received, installed AND used in a meaningful way during the project period.
FALSE |  | · | If any intellectual property resulted from the project, ensure that you have filed a disclosure form with ORI. Please refer to:
> Submit an Invention
30 DAYS PRIOR TO AWARD END DATE
Repeat 60-30 day steps
FALSE |  | · | Shut down p-card.
FALSE |  | · | Terminate internal cost center charges (e.g., animal care, etc.).
FALSE |  | · | Notify purchasing if any phones are associated that need to be shut down.
FALSE |  | · | Very closely examine the invoicing of your subawardees and consultants. Ensure that their billing is up to date and that they are positioned to submit final invoices at the required time. Clearly communicate when invoice is due.
FALSE |  | · | Submit any paperwork for personnel whose positions will be terminated at the end of the grant period.
FALSE |  | · | Clearly communicate reporting expectations and deadlines to subawardees
FALSE |  | · | Find the format for final reporting and engage all parties from whom you will need input. This may include technical reports, financial reports, invention reports, property management, etc.
PROJECT END DATE
FALSE |  | · | Make sure that you have stopped incurring new costs.
FALSE |  | · | Confirm you received a "final" invoice and processed it. Verfiy that total subaward expenditures reflect the cumulative expenditures on the final invoice.
FALSE |  | · | Continue to process invoices for costs incurred prior to the termial end date. This must be a priority and you must check to make sure all invoices have been processed.
FALSE |  | · | Carefully review your project statement as soon as it is available to ensure costs are complete and accurate so the university can collect funds for all expenditures.
FALSE |  | · | Know what the drop dead date is for final processing as any late expenses become the liability of the PI/their department.
FALSE |  | · | Finalize any required reports.
Note on F75: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Where is this being moved to? Do you want them to each have their own check box to the left?